## Actions
Action | Owner | Saving per machine (USD) | Investment (USD) | Gate | Status
Remove three machined datums from the frame | Tomas Lindqvist | 11000 | 0 | Alignment requalification | Approved
Five fan filter units with redesigned plenum | Ingrid Lund | 5500 | 18000 | 90 second box recovery measurement | Approved, gated
Rev B encoder selection | Nadia Haddad | 6000 | 200000 | Rev B schedule | Approved, funded Aug
Move harness assembly out of the clean bay | Greg Salinas | 9000 | 0 | Bagging procedure | Approved
Move frame assembly out of the clean bay | Greg Salinas | TBD | 0 | Process review with contamination control | September decision

## Cost Bridge
Line | Current (USD) | Target (USD) | Note
Standard cost per EFEM | 366000 | 334500 | After the four approved actions
List price | 620000 | 620000
Gross margin | 41% | 46% | Company target is 52%
Harmonic drive reducers (2) | 8400 | 8400 | Includes expedite premium
Linear encoder pair | 21000 | 15000 | Rev B
Ceramic blade set | 3100 | 3100 | No alternative supplier
Fan filter units (6) | 34000 | 28500 | Five units, gated on measurement
Frame weldment and machining | 58000 | 47000 | Three datums removed
Labour and cleanroom overhead | 62000 | 53000 | Harness relocation