## Revenue Plan
Quarter | Plan (USD) | Actual (USD) | Variance | Note
Q1 FY26 | 9800000 | 9640000 | -160000 | Kestrel units on plan
Q2 FY26 | 9300000 | 7760000 | -1540000 | Two Helios units moved out
Q3 FY26 | 13200000 |  |  | Helios FCS assumed 30 Sep
Q4 FY26 | 15900000 |  |  | Northgate production order assumed
FY26 total | 48200000

## R&D Spend
Line | Budget (USD) | Forecast (USD) | Owner | Note
Helios-3 NRE | 3600000 | 3600000 | Priya Raman | Includes Rev B controller spin
Kestrel-2 development | 2450000 | 2545000 | Tomas Lindqvist | Dry-break and auto-teach added
Vantage 4.0 | 2900000 | 2900000 | Elena Vasquez
Sustaining engineering | 1650000 | 1860000 | Priya Raman | Northgate excursion response 210k
Second source qualification | 0 | 140000 | Nadia Haddad | Halstead, approved 26 Mar
R&D total | 11400000 | 11905000 |  | 505k over plan

## Capex
Item | Budget (USD) | Spent (USD) | Status
ISO Class 5 assembly bay expansion | 2100000 | 400000 | Design and permits complete
Metrology: surfscan for incoming inspection | 340000 | 340000 | Installed
Kestrel life test rig | 85000 | 0 | Not started
Cleanroom gowning expansion | 60000 | 0 | Deferred

## Working Capital
Item | Value (USD) | Rationale
Cerapoint blade buffer stock (8 weeks, 46 blades) | 71000 | Approved 26 Mar against 13 week lead time
Kaneda reducer safety stock | 33600 | Four units
Brunnen encoder last-time-buy | TBD | Letter received; quantity not yet sized