# Helios-3 SEMI S2/S8 Certification Plan

Author: Claire Dubois

Date: 2026-04-17

Includes the results of the paper pre-assessment carried out in April 2026 against the SEMI S2 checklist, ahead of the production-intent build.

## 1. Scope of certification

SEMI S2 environmental, health and safety evaluation of the Helios-3 EFEM.

SEMI S8 ergonomics, evaluated in the same pass.

CE marking for European shipments: machinery directive and EMC directive, reusing the S2 technical file where permitted.

## 2. Schedule

| Milestone | Planned date | Dependency |
| --- | --- | --- |
| Paper pre-assessment complete | 2026-04-17 | Drawing set |
| Production-intent build in cleanroom | 2026-06-30 | Long lead parts |
| On-tool evaluation | July 2026 | Machine availability |
| Third party assessor on site | 2026-08-10 | Slot held, deposit paid |
| S2 report signed | 2026-08-28 | No major findings |
| EMC test at accredited lab | 2026-07-21 | Provisional booking |

The assessor slot was booked in March at a deposit of USD 4,000, forfeited if the date moves. Booking eight weeks ahead of a machine that did not yet exist was a deliberate decision taken on 12 March 2026.

## 3. Pre-assessment findings

| Ref | Section | Finding | Severity | Status |
| --- | --- | --- | --- | --- |
| PA-01 | Hazardous energy isolation | Vacuum generator supply not covered by the main disconnect | Major | Closed in Rev D drawings |
| PA-02 | Safeguarding | Interlocks fully bypassed in teach mode; arm can move at full speed | Major | Closed: reduced speed enforced in firmware plus hold-to-run pendant |
| PA-03 | Seismic | Restraint calculation not signed by a structural engineer | Major | Open: engineering firm queue is three weeks |
| PA-04 | Ergonomics (S8) | Load port teach position requires sustained overhead reach | Minor | Closed: service platform added |
| PA-05 | Documentation | Material declarations missing for approximately 40 suppliers | Minor | Open: supply chain collecting |
| PA-06 | Emergency off | EMO does not remove power from the ioniser | Minor | Closed in Rev D drawings |

Fourteen findings were raised in the pre-assessment. Eleven were closed in the drawing set before the build, which is the entire purpose of running a paper pass in April rather than discovering the same findings on a built machine in August.

## 4. Risk to the programme

The certification schedule has no float. A major finding at the on-tool assessment implies a design change, a rebuild of the affected subsystem and a re-evaluation of that section, which adds three to five weeks. The single production-intent machine is shared between engineering verification and the S2 evaluation, and approximately three of the eight evaluation weeks require exclusive access to it.