## Long Lead Items
Part | Supplier | Qty per machine | Unit cost (USD) | Lead time (weeks) | Source | Status
Harmonic drive reducer, theta | Kaneda Precision | 1 | 4200 | 22 | Single | On allocation, expedite approved
Harmonic drive reducer, R | Kaneda Precision | 1 | 4200 | 22 | Single | On allocation, expedite approved
Linear encoder head | Brunnen Motion | 2 | 10500 | 11 | Single | End of life, LTB by 2026-11-30
Ceramic edge grip blade CP-220 | Cerapoint Ceramics | 2 | 1550 | 13 | Single | Buffer stock 46 units
Fan filter unit, ISO Class 2 | Aldera Air | 6 | 5700 | 8 | Dual | Plenum redesign under evaluation
Frame weldment, machined | Kestone Fabrication | 1 | 58000 | 9 | Dual | Three datums removed in cost down
Z axis linear motor | Brunnen Motion | 1 | 7900 | 10 | Single
Wafer mapping sensor | Optivia Sensing | 1 | 2300 | 6 | Dual
Ioniser bar | Aldera Air | 2 | 890 | 4 | Dual
Controller board Rev A | In house | 1 | 3400 | 12 | Internal | Rev B in development

## Second Source Status
Part | Alternate supplier | Qualification cost (USD) | Duration | Blocker | Target complete
Harmonic drive reducer | Halstead Drive | 140000 | 5 months | Catalogue backlash 1 arc-min vs 0.7 required | Q1 2027
Ceramic edge grip blade | None identified |  |  | Three shops worldwide can hold the chamfer
Linear encoder head | Replacement selected in Rev B | 0 |  | Rev B schedule | 2026-12
Fan filter unit | Qualified | 0 |  | None | Complete

## Build Rate Constraint
Month | Plan (machines) | Reducer supply (machines) | Cleanroom capacity (machines) | Achievable
2026-09 | 5 | 3 | 4 | 3
2026-10 | 6 | 3 | 4 | 3
2026-11 | 7 | 3 | 4 | 3
2026-12 | 7 | 3 | 4 | 3
2027-01 | 8 | 3 | 7 | 3
2027-02 | 8 | 3 | 7 | 3