## Slide 1: Helios-3 Program Status — May 2026
Prepared by: Marcus Feld
Customer-facing status deck, issued 12 May 2026
Distribution: Northgate Micro equipment engineering
Notes: Customer-facing. Do not include internal cost or supplier names.

## Slide 2: Program Summary
300 mm atmospheric wafer handler and EFEM
Design frozen March 2026; end effector is Cerapoint alumina edge grip
Production-intent build in cleanroom 30 June 2026
First customer ship 30 September 2026

## Slide 3: Specification vs Plan of Record
Parameter | Committed | Status
Throughput | 450 wafers/hour | On plan
Particle adders (0.05 um, per pass) | <= 3 | 1.8 measured
Teach repeatability | +/- 25 um | Met
Mean cycles between interventions | 500,000 | Modelled
SEMI S2 / S8 report | End August 2026 | On plan
Notes: Throughput figure is the committed number from the January kickoff, not a measurement. Engineering measurement checkpoint is scheduled for June.

## Slide 4: April Particle Excursion — Closed
Backside particle excursion on the pilot tool, 7-15 April
Two causes: ceramic blade chamfer out of specification (supplier lot CP-220-0413) and an EFEM top plate gasket gap
Corrective actions: 100% incoming chamfer inspection for three lots, top plate fastener change, field rework kit for four machines
Tool returned to service 15 April at 2.1 backside adders per pass
Notes: 8D issued to the customer 30 April. Formal customer closure still pending as of this deck.

## Slide 5: Acceptance Criteria
Site acceptance test: 10 working days after install
Particle acceptance measured end to end across nine passes
SEMI S2 report included in the acceptance package
Vantage connectivity demonstrated as part of acceptance
Notes: The Vantage line was added at the customer's request during the April escalation call.

## Slide 6: Risks
Kaneda harmonic drive reducers on allocation; expedite premium approved
Cerapoint ceramic blades single source, 13 week lead time
Certification schedule has no float after the build