## Slide 1: Northgate Micro Escalation Review
Prepared by: Aisha Bello
Internal review, 24 April 2026
Escalation opened 7 April, tool recovered 15 April

## Slide 2: Impact
Pilot Helios-3 handler down four days
Three lots on hold, 75 wafers: 31 scrapped, 44 reworked and passed
Customer measured 22 backside adders at 0.05 um against a limit of 5
Production order for eleven EFEMs now contingent on a clean 90 day run
Notes: Ryan Chen's probability on the production order moved from 85% to 60% after this escalation.

## Slide 3: Response Timeline
Date | Event
7 Apr | Customer metrology flags excursion; tool down
9 Apr | Escalation bridge opened; daily cadence agreed
10 Apr | Contamination control engineer on site
13 Apr | Blade swap and gasket rework performed on site
15 Apr | Send-ahead wafers at 2.1 backside adders; tool released
16 Apr | Root cause review; two causes confirmed
30 Apr | 8D report issued to customer

## Slide 4: Commercial Settlement
USD 60,000 service credit
Two additional preventive maintenance visits at no charge
No wafer-value compensation offered; liability capped at tool value
Notes: Authorised by Priya Raman and Yuki Tanaka. Account team instructed not to move the number.

## Slide 5: What We Would Do Differently
Measure incoming chamfer rather than accept a certificate of conformance
Retained samples per lot made the root cause findable in five days
Send an engineer on day one; the travel cost was trivial against the risk